## Slide 1
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 12th June
Functions Login, FAQ, Contact Us, UI, Authentication
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
13th June – 26th June
Milestone FYP Proposal – 15th June 2015
Functions Data Recording, Business Calendar
Documentation Test Cases, Update Wiki, Update Bug log
27th June – 10th July
Functions Local iOS Storage (Sync), Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
11th July – 24th July
Functions User Access Control (For employees at multiple branches), Analytics (Graphical)
Documentation Test Cases, Update Wiki, Update Bug log
19th September – 2nd October
Functions Login with fingerprints
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
25th July – 7th August
UAT 1
Client Review
Functions Analytics (Analysis – e.g. forecasting peak period), Image Capturing
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides, Document UAT 1 Results
22nd August – 4th September
Functions Multiple Languages (English, Chinese and maybe Malay)
Documentations Test Cases, Update Wiki, Update Bug log
8th Aug – 21st August
Milestone 1) FYP Acceptance – 10th Aug 2) Registration and Class – 18th Aug
Functions Analytics (Analysis)
Documentation Test Cases, Update Wiki, Update Bug log
5th September – 18th September
UAT 2
Client Review
Functions Backend Admin Dashboard
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 2 Results
3rd October – 16th October
Milestone Midterm (3rd Oct – 7th Oct)
Functions Push notification to remind users to record
Documentation Test Cases, Update Wiki, Update Bug log
17th October – 30th October
UAT 3
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT Results
31st October – 13th November
Milestone Poster – 07th Nov 2016
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th November – 27th November
Milestone Final (21st Nov – 30th Nov 2016)
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th November – 2nd December
Milestone Poster day – 2nd Dec 2016, 1130 - 1430
Documentation Test Cases, Update Wiki, Update Bug log

## Slide 2
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration