## Bug Metrics
Bug Metrics
| Severity | Description |  | Points in Iteration | Action
| Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. |  | Points=<5 | Fix during buffer time only
| High Impact (5 points) | The system runs. However, some non-critical functionalities are not working. |  | 5 < Points <= 10 | Use the planned debugging time.
| Critical Impact (10 points) | The system is down or is unusable after a short period of time. We have to fix the bugs to continue. |  | Points>10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Bugs Found (End Iteration) | 4 | 15 | 6 | 7 | 10 | 18 | 38 | 3

## Bugs Log
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 1 | Authentication/ Registration | Error messages should start with capital letter. Several messages started with small lettersm resulting in inconsistency | Low | 1 | PUSHED | DONE | 1 | 19th June | 20th June
2 |  | Authentication/ Registration | If email address is in database already, by changing domain name to caps will still enable the user to register (i.e smarthawker@gmail.com & smarthawker@GMAIL.com should be considered the same email and not be allowed to register | High | 5 | YES | DONE |  | 19th June | 19th June
3 |  | Authentication/ Registration | Used "321" (3 digits) for admin pin and account can still be created even though not 4 digits | High | 5 | YES | DONE |  | 19th June | 19th June
4 |  | Authentication/ Registration | If 2 required fields are empty, it currently only shows the error of topmost empty field. | Low | 1 | PUSHED | DONE | 1 | 19th June | 22nd June
5 |  | Authentication/ Registration | Username shorter than 6 characters should not be able to register | High | 5 | YES | DONE |  | 19th June | 19th June
6 |  | Authentication/ Registration | Tested different password & confirm password field to get error message shown, however error message remain after problem being resolved. (i.e error message shown at bottom of page do not disappear BUT still can create acc) | Low | 1 | PUSHED | DONE | 1 | 19th June | 22nd June
7 |  | Authentication/ Registration | Change error message "Please enter confirm password" to "Please confirm password" | Low | 1 | PUSHED | DONE | 1 | 19th June | 20th June
8 |  | Authentication/ Registration | Photos taken using back camera will show error message “Photo taken not within 10mb” | High | 5 | YES | DONE |  | 19th June | 19th June
End Iteration 1 Total Bug Score | [7 empty] | 4
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 2 | Recording Module | When submitting record on a new date for the first time, the app will crash and may result in duplicate records (eg. 3 times logging of sales: $680, 2 times logging of cogs). Profit computed is inaccurate | Critical | 10 | YES | DONE |  | 3rd July | 3rd July
2 |  | Recording Module | When submitting 3rd record on the same day with blank revenue & COGS, the app crashed and may result in duplicate records (eg. 3 times logging of sales: $680, 2 times logging of cogs). Profit computed is inaccurate | Critical | 10 | YES | DONE |  | 3rd July | 3rd July
3 |  | Recording Module | When field is blank, it is not shown in view records. When field is "0" it shows up in records. | High | 5 | YES | DONE |  | 3rd July | 3rd July
4 |  | Recording Module | View records should be sorted by recording entry. (i.e Record 1, Record 2, Record 3) | High | 5 | PUSHED | DONE | 5 | 3rd July | 5th July
5 |  | Recording Module | When a field is edited in view records, it does not immediately reflect in view records page. Have to "back" to previous page to see the changes. | High | 5 | YES | DONE |  | 3rd July | 3rd July
6 |  | Recording Module | After deleting an entry in view records, it should remain in the same page instead of jumping back to new records page. 1) ENTRY is deleted but will redirect to add new records page instead of staying at "view records" page (hard to delete multiple records). 2) clicking back to "view all records", ENTRY will display as 0. Have to do it again before the record disappears | High | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
7 |  | Recording Module | Change New Record fields to: Revenue ($): COGs ($): Other Expenses ($): | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
8 |  | Recording Module | Change Record Format to : Total Revenue ($): Total COGS ($): Total Other Expenses ($): ------------------------------------------------------ Total Recorded Profit ($): | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
9 |  | Recording Module | Change Record Colour Format to : Total Revenue ($): BLACK Total COGS ($): (RED) Total Other Expenses ($): (RED) ------------------------------------------------------ Total Recorded Profit ($): PROFIT: GREEN, LOSS: RED | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
10 |  | Recording Module | Change date, day format to: EG. "03/07/2016" to "3rd July 2016, Sunday" | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
11 |  | Recording Module | Change "Click here to view all records" to "View All Records" | Low | 1 | YES | DONE |  | 3rd July | 3rd July
12 |  | Recording Module | Error message for blank & '0' in add new records should be in red. Error Message shouldn't disappear after 1-2 sec. | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
13 |  | Recording Module | SALES in "view all reports" change to REVENUE | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
14 |  | Recording Module | EXPENSES in "view all reports" change to OTHER EXPENSES | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
15 |  | Recording Module | Revenue, COGS and Other Expenses in "View All Records" are jumbled up and not in order | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
16 |  | Business Calendar | When user successfully recorded entry, the specific date in the Business Calendar would be higlighted according to the specific date. | Low | 1 | PUSHED | DONE | 1 | 3rd July | 5th July
End Iteration 2 Total Bug Score | [7 empty] | 15
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 |  | Tax Calculation | Rounding of decimals off ( more than 2 dp ) | Low | 1 | PUSHED | DONE | 1 | 2016-07-17 | 2016-07-18
2 |  | Tax Calculation | Cannot press the back button from tax calculation, only can navigate from tabs | High | 5 | PUSHED | DONE | 5 | 2016-07-17 | 2016-07-18
End Iteration 3 Total Bug Score | [7 empty] | 6
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 4 | Business Calendar/UI | Now selected date of the month remain while changing months, Some days don’t have the specific date, eg. Feb don’t have 31st. Not consistent | Low | 1 | PUSHED | DONE | 1 | 2016-07-30 | 1st August
2 |  | Business Calendar/UI | When existing records are deleted, a message should show ""You havn't added a record for the day", but it did not appear | Low | 1 | PUSHED | DONE | 1 | 2016-07-30 | 1st August
3 |  | Recording Module | When adding fixed expense, UI shouldn't show the record under daily. | High | 5 | PUSHED | DONE | 5 | 2016-07-30 | 1st August
End Iteration 4 Total Bug Score | [7 empty] | 7
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 5 | Business Calendar | Calendar may have unexpected crashes | Critical | 10 | YES | DONE |  | 14th Aug | UI Revamp,
2 |  | Main Page/ UI | "Average Sales" figure out of box | Low | 1 | YES | DONE |  | 14th Aug
3 |  | Analytics / UI | When scrolling up/down, the contents will intersect the header | Low | 1 | YES | DONE |  | 14th Aug
4 |  | Recording, Biz Calendar/ UI | "Profit" values out of box | Low | 1 | YES | DONE |  | 14th Aug
5 |  | Edit Profile | When changing profile photo with picture taken with camera, it does not update | High | 5 | PUSHED | NIL | 5 | 14th Aug
6 |  | Edit Profile | When changing email to one that has already been taken, it still allowed saved when it should not | High | 5 | PUSHED | NIL | 10 | 14th Aug
End Iteration 5 Total Bug Score | [7 empty] | 10
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 6 | Edit Profile | Edit profile button missing tab and back button, unable to navigate back or tab to other places | Critical | 10 | PUSHED | DONE | 10 | 28th Aug | 29th Aug
2 |  | Recording | Add description tab input does not start with caps | Low | 1 | PUSHED | DONE | 1 | 28th Aug | 29th Aug
3 |  | Main Page | Set monthly target and add new record labels are not standardised in home tab. | Low | 1 | PUSHED | DONE | 1 | 28th Aug | 29th Aug
4 |  | Main Page | Fonts in home tab too small. | Low | 1 | PUSHED | DONE | 1 | 28th Aug | 29th Aug
5 |  | Main Page | Added new record, but date cannot change. Either able to change date or change name from "Add new record" to “Add today’s record” | High | 5 | PUSHED | DONE | 5 | 28th Aug | 29th Aug
End Iteration 6 Total Bug Score | [7 empty] | 18
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 7 | Recording | Expenses tab, change "Other expenses" to "Other Expenses” | Low | 1 | PUSHED | DONE | 1 | 11th Sept | 12th Sept
2 |  | Recording, Report | Calendar and Report view VALUES don’t tally. Report show missing values | Critical | 10 | PUSHED | DONE | 10 | 11th Sept | 12th Sept
3 |  | Recording | Each daily record should be displayed in the following sequence - Sales, COGS, Expenses, Profit. Inconsistent display sequence of items | High | 5 | PUSHED | DONE | 5 | 11th Sept | 12th Sept
4 |  | Recording | Remove Edit Table | Low | 1 | YES | DONE |  | 11th Sept | 12th Sept
5 |  | Report | Report “week” sales graph have error. Shows accumlated sales instead of individual sales | High | 5 | PUSHED | DONE | 5 | 11th Sept | 12th Sept
6 |  | Report | For ‘Week, Month & Year’ in report, the COGS is lumped together under ‘Total Expenses’. Separate it into another Total COGS. Include highest & lowest - Sales, COGS, Expenses & Profit figures in the graph/chart | High | 5 | PUSHED | DONE | 5 | 11th Sept | 12th Sept
7 |  | Income Tax | Change current fields to follow IRAS’sequence i) Revenue, ii) Gross Profit, iii) Allowable Business Expenses, iv) Adjusted Profit/Loss. | Low | 1 | PUSHED | DONE | 1 | 11th Sept | 12th Sept
8 |  | Income Tax | Add disclaimer that it is an estimated value | Low | 1 | PUSHED | DONE | 1 | 11th Sept | 12th Sept
9 |  | Main Page | Lowest Sales indicated as ‘$0’, should show lowest of all recorded sales instead | High | 5 | PUSHED | DONE | 5 | 11th Sept | 12th Sept
10 |  | Main Page | Last record if put future date, but only show current date record. Show most updated date instead, include future record date if added | Low | 1 | YES | DONE |  | 11th Sept | 12th Sept
11 |  | Edit Profile | Email edit field will say invalid. | High | 5 | PUSHED | DONE | 5 | 11th Sept | 12th Sept
End Iteration 7 Total Bug Score | [7 empty] | 38
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
1 | 8 | Registration | Registration cuts off at email entry – have to click ‘Done’ before phone & admin pin info can be keyed in | High | 5 | YES | DONE |  | 20th Sept | 22nd Sept
2 |  | Main Page | Break up the all-white background. | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
3 |  | Main Page | Increase font size of text and numbers | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
4 |  | Main Page | Show overview information of "Today's Figures", "This week's figures" and "This Month Figures" | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
5 |  | Report | Bold the ‘Net Profit’ line of text/info. | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
6 |  | Report | Amend legend under chart to this sequence – Total Sales, Total COGS, Total Expenses. | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
7 |  | Income Tax | Revenue – Insert ‘Total Sales’ in brackets underneath. | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
8 |  | Income Tax | Gross Profit – Amend bracketed info underneath to ‘Total Sales – Total COGS’. | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
9 |  | Income Tax | Allowable Business Expenses – Remove ‘(Optional)’; Amend bracketed info to ‘Please assess your Total Expenses and enter allowable amount. Check IRAS website if unsure.’ | Low | 1 | YES | DONE |  | 20th Sept | 22nd Sept
10 |  | Calendar | Lock the days of the week at the top of the screen. It appears & disappears during page scrolling. | High | 5 | YES | DONE |  | 20th Sept | 22nd Sept
11 |  | Registration | When confirm password don’t match, error msg should be “confirmed” instead of “confirm” | Low | 1 | PUSHED |  | 1 | 25th Sept
12 |  | Registration | When registration success msg should show "account” instead of "Account" | Low | 1 | PUSHED |  | 1 | 25th Sept
13 |  | Sync | When sync without wifi msg: change “a” to “an” | Low | 1 | PUSHED |  | 1 | 25th Sept
End Iteration 8 Total Bug Score | [7 empty] | 3
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved
End Iteration 9 Total Bug Score