## Slide 1
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module (I), Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto App Store
Functions Accounting Module (I) – User Access Control, Analytics Module (Graphical), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), Expert Testing (II) Review
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions Analytics Module (Analysis – e.g. forecasting peak period), Expert Testing (I) Review
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki

## Slide 2
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module (I), Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto Apple Test Flight
Functions Accounting Module (II) – User Access Control, Analytics Module (Graphical) (I)
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I)
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), Expert Testing Review (II)
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions Analytics Module (Analysis – e.g. forecasting peak period) (II), Expert Testing Review (I)
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki

## Slide 3
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module, Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto Apple Test Flight
Functions Authentication Module (I), BI Module (Graphical) (I)
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module (II)
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), BI Module (BI– e.g. best sales) (II), Expert Testing Review (II)
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions BI Module (BI– e.g. best sales) (II), Expert Testing Review (I)
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I)
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides

## Slide 4
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration
Changes