## Bug Metrics
Bug Metrics
Severity | Description | Points in Iteration | Action
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. | Points=<5 | Fix during buffer time only
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working. | 5 < Points < 10 | Use the planned debugging time.
Critical Impact (10 points) | The system is down or is unusable after a short period of time. We have to fix the bugs to continue. | Points>=10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bugs reporting
S/N | Iteration | Function | Description | Severity | Points | Total | Status | Date Discovered | Date Resolved | Debug Pair | Action Plan