## Task Metric scoring
Schedule Metrics
Score(%) | Mitigation Action
SM < 50 | 1. Immediately, inform your supervisor about the slip within 24 hours.
2. Then use the same mitigation as the category 50 < SM < 90 and seriously consider dropping tasks.
50 < SM <= 90 | 1. Re-estimate the tasks for future iterations.
2. Deduct the number of days behind schedule from buffer days.
3. If there is no more buffer day, decide the functionalities to drop.
90 < SM <= 110 | 1. Add/Deduct the number of days behind schedule from buffer days.
2. If there is no more buffer day, decide the functionalities to drop.
110 < SM <= 150 | 1. Re-estimate the task for future iterations.
2. Add the number of days gained to buffer days.
150 < SM | 1. Immediately inform your supervisor about the slip within 24 hours.
2. Then use the same mitigation as the category 110 < SM < 150.

## Task Metric
Task Metrics
Iteration | Total Number Task | Task Completed | Task to be brought to next iteration | Metrics
1
2
3
4
5
6
7
8
9
10
11
12