## Slide 1
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module (I), Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto App Store
Functions Accounting Module (I) – User Access Control, Analytics Module (Graphical), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), Expert Testing (II) Review
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions Analytics Module (Analysis – e.g. forecasting peak period), Expert Testing (I) Review
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki

## Slide 2
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module (I), Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto App Store
Functions Accounting Module (II) – User Access Control, Analytics Module (Graphical), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), Expert Testing (II) Review
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions Analytics Module (Analysis – e.g. forecasting peak period), Expert Testing (I) Review
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki

## Slide 3
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 19th Jun
Milestone FYP Proposal: 15th June
Functions Accounting Module, Online Help Module
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
20th Jun – 3rd Jul
Functions Recording Module – Data Recording, Business Calendar Module
Documentation Test Cases, Update Wiki, Update Bug log
4th Jul – 17th Jul
Functions Offline Mode Module, Recording Module - Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
18th Jul – 31st Jul
Milestone Uploading onto App Store
Functions Authentication Module (I), Analytics Module (Graphical), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Expert Testing User Guide
26th Sep – 9th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Authentication Module (II)
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
1st Aug – 14th Aug
Milestone (1) FYP Acceptance: 10th Aug
Expert Testing (I)
Functions Language Module (I), Revamp UI
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides
29th Aug – 11th Sep
Functions Image Capturing Module, Language Module (II), Analytics Module (Analysis – e.g. forecasting peak period), Expert Testing (II) Review
Expert Testing (II)
Documentations Test Cases, Update Wiki, Update Bug log
15th Aug – 28th Aug
Milestone (2) Registration and Class: 18th Aug
Functions Analytics Module (Analysis – e.g. forecasting peak period), Expert Testing (I) Review
Documentation Test Cases, Update Wiki, Update Bug log, Document Expert Testing Results
12th Sep – 25th Sep
UAT 1
Client Review
Functions Push Notification Module
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 1 Results
10th Oct – 23rd Oct
Functions Backend Admin Module
Documentation Test Cases, Update Wiki, Update Bug log
24th Oct– 6th Nov
UAT 2
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 2 Results
7th Nov – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Final: 21st Nov – 30th Nov Poster day: 2nd Dec
Documentation Update Wiki

## Slide 4
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration
Changes