## Functions
| Done |  | In Charge
Functions | Authentication Module (I) Enquiry Module (FAQ) Data Recording Module Business Calendar Module Local Storage Module Tax Calculation Module Analytics Module II (Graphical) |  | Wei Lun, Zong Wei
| Not Done | Due Date
Functions | User Access Control Module (Due by Acceptance)
Language Module I and II
Analytics Module II (Analysis - e.g. forecasting peak period)
Image Capturing Module
Backend Admin Module
Push Notification Module

## UI UX
| Done |  | In Charge
UI | Login/Sign Up |  | Gao Min, Wendy
| Not Done | Due Date
UI

## Testing
| Done |  | In Charge
Testing |  |  | Ching Yi
| Not Done | Due Date
Testing

## Documentation
Done |  | In Charge
External meeting minutes 1-7 Meet Ben Gan's slides
Not Done | Due Date
Supervisor meeting minutes | 24th July 2016 | Wendy
FYP Acceptance Slides | 3rd Aug 2016 | Wendy
Internal meeting minutes 1-8 | 8th Aug 2016 | Wendy and Weilun
User guide | 24th July 2016