## Slide 1
00
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15th May – 29th May
Requirement Gathering
Crafting Survey Questionnaire
Explore Android
30th May – 12th June
Functions Login, FAQ, Contact Us, UI, Authentication
Documentations FYP Proposal, Wiki Page, Test Cases, Bug log
13th June – 26th June
Milestone FYP Proposal: 15th June
Functions Data Recording, Business Calendar
Documentation Test Cases, Update Wiki, Update Bug log
27th June – 10th July
Functions Local iOS Storage (Sync), Tax Calculation
Documentation Test Cases, Update Wiki, Update Bug log
11th July – 24th July
Functions User Access Control (For employees at multiple branches), Analytics (Graphical)
Documentation Test Cases, Update Wiki, Update Bug log
19th Sep – 2nd Oct
Functions Login with fingerprints
Documentations Test Cases, Update Wiki, Update Bug log, Prepare for Midterm Slides
25th July – 7th Aug
UAT 1
Client Review
Functions Analytics (Analysis – e.g. forecasting peak period), Image Capturing
Documentation Test Cases, Update Wiki, Update Bug log, Prepare acceptance slides, Document UAT 1 Results
22nd Aug – 4th Sep
Functions Multiple Languages (English, Chinese and maybe Malay)
Documentations Test Cases, Update Wiki, Update Bug log
8th Aug – 21st Aug
Milestone (1) FYP Acceptance: 10th Aug (2) Registration and Class: 18th Aug
Functions Analytics (Analysis)
Documentation Test Cases, Update Wiki, Update Bug log
5th Sep – 18th Sep
UAT 2
Client Review
Functions Backend Admin Dashboard
Documentation Test Cases, Update Wiki, Update Bug log, Document UAT 2 Results
3rd Oct – 16th Oct
Milestone Midterm: 3rd Oct – 7th Oct
Functions Push notification to remind users to record
Documentation Test Cases, Update Wiki, Update Bug log
17th Oct– 30th Oct
UAT 3
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Finalize Poster, Document UAT 3 Results
31st Oct – 13th Nov
Milestone Poster: 7th Nov
Client Review
Buffer Iteration
Documentation Test Cases, Update Wiki, Update Bug log, Prepare finals presentation
14th Nov – 27th Nov
Milestone Final: 21st Nov – 30th Nov
Documentation Test Cases, Update Wiki, Update Bug log, Prepare for poster day, User Manual
28th Nov – 2nd Dec
Milestone Poster day: 2nd Dec
Documentation Test Cases, Update Wiki, Update Bug log

## Slide 2
= Iteration Number
User Test
Milestones
Client Review
Buffer Iteration