## Bug Metrics
Bug Metrics
| Severity | Description |  | Points in Iteration | Action
| Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. |  | Points=<5 | Fix during buffer time only
| High Impact (5 points) | The system runs. However, some non-critical functionalities are not working. |  | 5 < Points < 10 | Use the planned debugging time.
| Critical Impact (10 points) | The system is down or is unusable after a short period of time. We have to fix the bugs to continue. |  | Points>=10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
Iteration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Bugs Found (End Iteration) | 6 | 15

## Bugs Log
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved | Action Plan
1 | 1 | Authentication/ Registration | Error messages should start with capital letter. Several messages started with small lettersm resulting in inconsistency | Low | 1 | NO | DONE | 1 | 19th June | 20th June
2 |  | Authentication/ Registration | If email address is in database already, by changing domain name to caps will still enable the user to register (i.e smarthawker@gmail.com & smarthawker@GMAIL.com should be considered the same email and not be allowed to register | High | 5 | YES | DONE | 1 | 19th June | 19th June
3 |  | Authentication/ Registration | Used "321" (3 digits) for admin pin and account can still be created even though not 4 digits | High | 5 | YES | DONE | 1 | 19th June | 19th June
4 |  | Authentication/ Registration | If 2 required fields are empty, it currently only shows the error of topmost empty field. | Low | 1 | NO | DONE | 2 | 19th June | 22nd June
5 |  | Authentication/ Registration | Username shorter than 6 characters should not be able to register | High | 5 | YES | DONE | 2 | 19th June | 19th June
6 |  | Authentication/ Registration | Tested different password & confirm password field to get error message shown, however error message remain after problem being resolved. (i.e error message shown at bottom of page do not disappear BUT still can create acc) | Low | 1 | NO | DONE | 3 | 19th June | 22nd June
7 |  | Authentication/ Registration | Change error message "Please enter confirm password" to "Please confirm password" | Low | 1 | NO | DONE | 4 | 19th June | 20th June
8 |  | Authentication/ Registration | Photos taken using back camera will show error message “Photo taken not within 10mb” | High | 5 | YES | DONE | 4 | 19th June | 19th June
9 |  | Pre-login landing/ UI | Logo to change to Smart Hawker logo | Low | 1 | NO | DONE | 5 | 19th June
10 |  | Pre-login landing/ UI | Copyright info display should "SmartHawker © 2016" instead of "SmartHawker © 2015" | Low | 1 | NO | DONE | 6 | 19th June
End Iteration 1 Total Bug Score | [7 empty] | 6
S/N | Iteration | Function | Description | Severity | Points | Resolved by End Iteration? | Status | Total | Date Discovered | Date Resolved | Action Plan
1 | 2 | Recording Module | When submitting record on a new date for the first time, the app will crash and may result in duplicate records (eg. 3 times logging of sales: $680, 2 times logging of cogs). Profit computed is inaccurate | Critical | 10 | YES | DONE | 0 | 3rd July | 3rd July
2 |  | Recording Module | When submitting 3rd record on the same day with blank revenue & COGS, the app crashed and may result in duplicate records (eg. 3 times logging of sales: $680, 2 times logging of cogs). Profit computed is inaccurate | Critical | 10 | YES | DONE | 0 | 3rd July | 3rd July
3 |  | Recording Module | When field is blank, it is not shown in view records. When field is "0" it shows up in records. | High | 5 | YES | DONE | 0 | 3rd July | 3rd July
4 |  | Recording Module | View records should be sorted by recording entry. (i.e Record 1, Record 2, Record 3) | High | 5 | NO |  | 5 | 3rd July
5 |  | Recording Module | When a field is edited in view records, it does not immediately reflect in view records page. Have to "back" to previous page to see the changes. | High | 5 | YES | DONE | 5 | 3rd July | 3rd July
6 |  | Recording Module | After deleting an entry in view records, it should remain in the same page instead of jumping back to new records page. 1) ENTRY is deleted but will redirect to add new records page instead of staying at "view records" page (hard to delete multiple records). 2) clicking back to "view all records", ENTRY will display as 0. Have to do it again before the record disappears | High | 1 | NO |  | 6 | 3rd July
7 |  | Recording Module | Change New Record fields to: Revenue ($): COGs ($): Other Expenses ($): | Low | 1 | NO | DONE | 7 | 3rd July
8 |  | Recording Module | Change Record Format to : Total Revenue ($): Total COGS ($): Total Other Expenses ($): ------------------------------------------------------ Total Recorded Profit ($): | Low | 1 | NO | DONE | 8 | 3rd July
9 |  | Recording Module | Change Record Colour Format to : Total Revenue ($): BLACK Total COGS ($): (RED) Total Other Expenses ($): (RED) ------------------------------------------------------ Total Recorded Profit ($): PROFIT: GREEN, LOSS: RED | Low | 1 | NO | DONE | 9 | 3rd July
10 |  | Recording Module | Change date, day format to: EG. "03/07/2016" to "3rd July 2016, Sunday" | Low | 1 | NO | DONE | 10 | 3rd July
11 |  | Recording Module | Change "Click here to view all records" to "View All Records" | Low | 1 | YES | DONE | 10 | 3rd July | 3rd July
12 |  | Recording Module | Error message for blank & '0' in add new records should be in red. Error Message shouldn't disappear after 1-2 sec. | Low | 1 | NO |  | 11 | 3rd July
13 |  | Recording Module | SALES in "view all reports" change to REVENUE | Low | 1 | NO | DONE | 12 | 3rd July
14 |  | Recording Module | EXPENSES in "view all reports" change to OTHER EXPENSES | Low | 1 | NO | DONE | 13 | 3rd July
15 |  | Recording Module | Revenue, COGS and Other Expenses in "View All Records" are jumbled up and not in order | Low | 1 | NO |  | 14 | 3rd July
16 |  | Business Calendar | When user successfully recorded entry, the specific date in the Business Calendar would be higlighted according to the specific date. | Low | 1 | NO |  | 15 | 3rd July
End Iteration 2 Total Bug Score | [7 empty] | 15