## Functions
| Done |  | In Charge
Functions | Authentication Module (I) Enquiry Module (FAQ) Business Calendar Module Tax Calculation Module Analytics Module I (Graphical) |  | Wei Lun, Zong Wei
| Not Done | Due Date
Functions | User Access Control Module (Due by Acceptance) | 24th July 2016
| Language Module I and II | 23rd July 2016
| Analytics Module II (Analysis - e.g. forecasting peak period) | 22nd August 2016
| Image Capturing Module | 4th September 2016
| Backend Admin Module | 24th September 2016
| Push Notification Module | 17th October 2016
| Data Recording Module | 23rd July 2016
| Local Storage Module | 23rd July 2016

## UI UX
| Done |  | In Charge
UI | Login/Sign Up |  | Gao Min, Wendy
| Not Done | Due Date
UI

## Testing
| Done |  | In Charge
Testing |  |  | Ching Yi
| Not Done | Due Date
Testing

## Documentation
Done |  | In Charge
External meeting minutes 1-7 Meet Ben Gan's slides
Not Done | Due Date
Supervisor meeting minutes | 24th July 2016 | Wendy
FYP Acceptance Slides | 3rd Aug 2016 | Wendy
Internal meeting minutes 1-8 | 8th Aug 2016 | Wendy and Weilun
User guide | 24th July 2016
API documentation

## UAT
UAT | Things to prepare checklist | Deadline | Status
1 | User Manual
Contact List
2 | User Manual
Contact List